## WBS with Gantt Chart BLANK
WORK BREAKDOWN STRUCTURE WITH GANTT CHART
PROJECT TITLE |  | End-to-End C++ Application Development |  |  |  |  | COMPANY NAME | [8 empty] | Nokia
PROJECT MANAGER |  | Team Nokia |  |  |  |  | DATE | [8 empty] | 2022-04-15
PHASE ONE
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
Level 1 | Team Forming and Project Choice
1.1 | Forming the team | Team members | 2022-02-21 | 2022-03-18 | 25 | 100% | bar: WEEK 1 Th
| Project Choice | Team members | 2022-03-06 | 2022-03-18 | 12 | 100% | bar: WEEK 2 M to WEEK 2 F
| Project Theme | Team members | 2022-03-06 | 2022-03-18 | 12 | 100% | bar: WEEK 3 M to WEEK 4 F
Level 2 | Project planning
| Research | Team members | 2022-03-21 | 2022-03-26 | 5 | 100% | bar: WEEK 5 M to WEEK 5 F
| Schedules | Ciucioiu Roxana | 2022-03-28 | 2022-03-31 | 3 | 90% | bar: WEEK 6 M to WEEK 6 W
| Project documentation | Team members | 2022-03-31 | 2022-04-14 | 14 | 80% | bar: WEEK 6 Th to WEEK 8 W
| Project initiation | Team members | 2022-04-14 | 2022-04-16 | 2 | 100% | bar: WEEK 8 Th to WEEK 8 F
Level 3 | Project requirements and interfaces
| General functionalities | Budurean Mihai | 2022-04-04 | 2022-05-03 | 29 | 25% | bar: WEEK 7 M to WEEK 10 T
| Additional functionalities | Borza Radu | 2022-04-04 | 2022-05-03 | 29 | 25% | bar: WEEK 7 M to WEEK 10 T
| Testing system | Bogdan Emilian | 2022-04-04 | 2022-05-03 | 29 | 25% | bar: WEEK 7 M to WEEK 10 T
| Interface | Team members | 2022-05-02 | 2022-05-13 | 11 | 0% | bar: WEEK 10 M to WEEK 11 F
Level 4 | Project Performance/Monitoring
| Bug fixes | Budurean Mihai, Borza Radu, Bogdan Emilian | 2022-05-09 | 2022-05-30 | 16 | 0% | bar: WEEK 11 M to WEEK 14 M
| Documentation Review | Ciucioiu Roxana | 2022-02-21 | 2022-05-27 | 95 | 57% | bar: WEEK 1 F; WEEK 2 F; WEEK 3 F; WEEK 4 F; WEEK 5 F; WEEK 6 F; WEEK 7 F; WEEK 8 F; WEEK 9 F; WEEK 10 F; WEEK 11 F; WEEK 12 F; WEEK 14 M
| Final Presentation | Team Members | 2022-05-31 | 2022-05-31 | 1 | 0% | bar: WEEK 14 T
CLICK HERE TO CREATE WBS OUTLINE AND DIAGRAM TEMPLATES IN SMARTSHEET | bar: WEEK 1 M to WEEK 12 F